## All Failed Inspections
Discipline | Inspection Outcome | Inspection Type | Failure Date | Days Since Failure | Address | Quadrant | Community | Deficiency Text | Trade Contractor | Applicant | Project Cost | Project Description | Permit Class | Work Class | Permit Status | Parent BP Permit ID | Parent BP Match | Job Type | Mega Project Flag | Tax Appeal Pending? | Federal Vendor? | AGLC Licence At Address? | Federal Sole-Source Vendor? | Recently Opened Here?
Building Deficiencies | Not Acceptable | Final | 2026-05-08 | 6 | 49A MONTROSE CR NE | NE |  | Building was locked at time of inspection. No inspection was conducted. No access, multiple attempts made to gain access and contact builder. SCO phoned 3 different contacts associated with project on previous bookings. SCO expiring building permit. |  |  | 0 |  |  |  |  | BP2022-01720 | NO | Residential Improvement Project
Building Deficiencies | Not Acceptable | Final | 2026-05-05 | 9 | 339 46 AV SW | SW |  | Electrical compliance is required prior to occupancy. -EP is to be revised and completed. |  |  | 0 |  |  |  |  | BP2022-11814 | NO | Residential Improvement Project
Building Deficiencies | Not Acceptable | Progress | 2026-04-29 | 15 | #5 4616 6A ST NE | NE | GREENVIEW INDUSTRIAL PARK | - Tire Storage 1) A tire storage area designed to contain more than 375 m3 of rubber tires shall be separated from the remainder of the building by a fire separation having a fire-resistance rating of not less than 2 h. (See Note A-3.3.6.5.(1).) No tires allowed to be stored on site. |  | LINDA AUTO & TIRES | 12000 | Interior alterations - Linda Auto & Tires | 3399 - Motor-Vehicle Misc. | Alteration | Completed | BP2025-21789 | YES | Commercial / Multi Family Project
Building Deficiencies | Not Acceptable | Progress | 2026-04-28 | 16 | 4655 82 ST NW | NW | BOWNESS | NBC AE Division B 9.8.7.7. Design and Attachment of Handrails Provide a graspable handrail to the exterior steps and the installed height shall be not less than 865 mm (34 1/16"), & not more than 965 mm (38") | CANSTRUX |  | 15000 | Interior Alteration - Exterior Alterations | 3799 - Personal Service. Misc. | Alteration | Completed | BP2026-02939 | YES | Commercial / Multi Family Project
Building Deficiencies | Not Acceptable | Progress | 2026-04-27 | 17 | #259C 6455 MACLEOD TR SW | SW | MEADOWLARK PARK | NBC AE Division B 3.1.17. Occupant Load - Provide a permanent sign posted in a conspicuous location indicating that the maximum occupant load is 58 people. |  |  | 1000000 | Interior Alterations - Restaurant | 3608 - Restaurant | Alteration | Completed | BP2025-17324 | YES | Commercial / Multi Family Project | YES
SAMPLE — only 5 rows shown, contact columns redacted. Subscribe at shovelradar.com/pricing for the full weekly feed.

## Building Deficiencies
Discipline | Inspection Outcome | Inspection Type | Failure Date | Days Since Failure | Address | Quadrant | Community | Deficiency Text | Trade Contractor | Applicant | Project Cost | Project Description | Permit Class | Work Class | Permit Status | Parent BP Permit ID | Parent BP Match | Job Type | Mega Project Flag | Tax Appeal Pending? | Federal Vendor? | AGLC Licence At Address? | Federal Sole-Source Vendor? | Recently Opened Here?
Building Deficiencies | Not Acceptable | Final | 2026-05-08 | 6 | 49A MONTROSE CR NE | NE |  | Building was locked at time of inspection. No inspection was conducted. No access, multiple attempts made to gain access and contact builder. SCO phoned 3 different contacts associated with project on previous bookings. SCO expiring building permit. |  |  | 0 |  |  |  |  | BP2022-01720 | NO | Residential Improvement Project
Building Deficiencies | Not Acceptable | Final | 2026-05-05 | 9 | 339 46 AV SW | SW |  | Electrical compliance is required prior to occupancy. -EP is to be revised and completed. |  |  | 0 |  |  |  |  | BP2022-11814 | NO | Residential Improvement Project
Building Deficiencies | Not Acceptable | Progress | 2026-04-29 | 15 | #5 4616 6A ST NE | NE | GREENVIEW INDUSTRIAL PARK | - Tire Storage 1) A tire storage area designed to contain more than 375 m3 of rubber tires shall be separated from the remainder of the building by a fire separation having a fire-resistance rating of not less than 2 h. (See Note A-3.3.6.5.(1).) No tires allowed to be stored on site. |  | LINDA AUTO & TIRES | 12000 | Interior alterations - Linda Auto & Tires | 3399 - Motor-Vehicle Misc. | Alteration | Completed | BP2025-21789 | YES | Commercial / Multi Family Project
Building Deficiencies | Not Acceptable | Progress | 2026-04-28 | 16 | 4655 82 ST NW | NW | BOWNESS | NBC AE Division B 9.8.7.7. Design and Attachment of Handrails Provide a graspable handrail to the exterior steps and the installed height shall be not less than 865 mm (34 1/16"), & not more than 965 mm (38") | CANSTRUX |  | 15000 | Interior Alteration - Exterior Alterations | 3799 - Personal Service. Misc. | Alteration | Completed | BP2026-02939 | YES | Commercial / Multi Family Project
Building Deficiencies | Not Acceptable | Progress | 2026-04-27 | 17 | #259C 6455 MACLEOD TR SW | SW | MEADOWLARK PARK | NBC AE Division B 3.1.17. Occupant Load - Provide a permanent sign posted in a conspicuous location indicating that the maximum occupant load is 58 people. |  |  | 1000000 | Interior Alterations - Restaurant | 3608 - Restaurant | Alteration | Completed | BP2025-17324 | YES | Commercial / Multi Family Project | YES
Building Deficiencies | Not Acceptable | Progress | 2026-04-21 | 23 | 2702 CENTRE ST NE | NE | TUXEDO PARK | NBC AE Division B 3.1.9.1. Firestops - Complete firestopping in exterior mechanical room, pipes behind furnace, and in the top right corner on the west wall. (All other areas completed, and these items were discussed with owner and general contractor.) |  |  | 400000 | Interior Alteration - Flavours Restaurant | 3608 - Restaurant | Alteration | Completed | BP2024-22153 | YES | Commercial / Multi Family Project
Building Deficiencies | Not Acceptable | Progress | 2026-04-16 | 28 | 2702 CENTRE ST NE | NE | TUXEDO PARK | 3.8.3.23. Parking Stalls 1) A parking stall intended for use by persons using a wheelchair or other mobility aid shall a) be designed as a 2.4 m wide parking stall adjacent to a 2.4 m wide access aisle where the access aisle is demarcated to indicate no parking, b) have a firm, slip-resistant and level surface, c) be clearly marked and identified by i) a vertically mounted sign, located near the centre line of each designated stall, with the centre of the sign between 1 600 to 2 500 mm from the finished surface, and ii) the International Symbol of Access painted on the pavement, d) be located adjoining a barrier-free path of travel leading to the nearest barrier-free entrance, |  |  | 400000 | Interior Alteration - Flavours Restaurant | 3608 - Restaurant | Alteration | Completed | BP2024-22153 | YES | Commercial / Multi Family Project
Building Deficiencies | Not Acceptable | Final | 2026-04-16 | 28 | 144 DOVERTHORN CL SE | SE |  | File complete upon receipt of required documents. - email SCO at the bottom of this report once p.eng review is uploaded. |  |  | 0 |  |  |  |  | BP2021-03010 | NO | Residential Improvement Project
Building Deficiencies | Not Acceptable | Progress | 2026-04-15 | 29 | 5858 SIGNAL HILL CE SW | SW | SIGNAL HILL | NBC AE Division C 2.4.1.1. General (P.Eng Review) -Provide as-built field review bearing the seal of the registered professional engineer of the tents and shade structures. |  |  | 80000 | Temporary Garden Centre - Real Canadian Superstore - RCSS 1577 | 3106 - Retail Shop | Temporary | Completed | BP2025-24159 | YES | Commercial / Multi Family Project |  | Yes |  |  |  | Yes

## Electrical Deficiencies
Discipline | Inspection Outcome | Inspection Type | Failure Date | Days Since Failure | Address | Quadrant | Community | Deficiency Text | Resolved | Resolved Date | Trade Contractor | Applicant | Project Cost | Project Description | Permit Class | Work Class | Permit Status | Parent BP Permit ID | Parent BP Match | Job Type | Mega Project Flag

## P&G Deficiencies
Discipline | Inspection Outcome | Inspection Type | Failure Date | Days Since Failure | Address | Quadrant | Community | Deficiency Text | Resolved | Resolved Date | Trade Contractor | Applicant | Project Cost | Project Description | Permit Class | Work Class | Permit Status | Parent BP Permit ID | Parent BP Match | Job Type | Mega Project Flag

## Repeat Offenders
Trade Contractor | Failures | Disciplines | Distinct Sites | Most Recent Failure | Total Project Value

## Daily Volume Trend
Date | Building Failures | Electrical Failures | P&G Failures | Total Failures
2026-04-15 | 1 | 0 | 0 | 1
2026-04-16 | 2 | 0 | 0 | 2
2026-04-17 | 0 | 0 | 0 | 0
2026-04-18 | 0 | 0 | 0 | 0
2026-04-19 | 0 | 0 | 0 | 0
2026-04-20 | 0 | 0 | 0 | 0
2026-04-21 | 1 | 0 | 0 | 1
2026-04-22 | 0 | 0 | 0 | 0
2026-04-23 | 0 | 0 | 0 | 0
2026-04-24 | 0 | 0 | 0 | 0
2026-04-25 | 0 | 0 | 0 | 0
2026-04-26 | 0 | 0 | 0 | 0
2026-04-27 | 1 | 0 | 0 | 1
2026-04-28 | 1 | 0 | 0 | 1
2026-04-29 | 1 | 0 | 0 | 1
2026-04-30 | 0 | 0 | 0 | 0
2026-05-01 | 0 | 0 | 0 | 0
2026-05-02 | 0 | 0 | 0 | 0
2026-05-03 | 0 | 0 | 0 | 0
2026-05-04 | 0 | 0 | 0 | 0
2026-05-05 | 1 | 0 | 0 | 1
2026-05-06 | 0 | 0 | 0 | 0
2026-05-07 | 0 | 0 | 0 | 0
2026-05-08 | 1 | 0 | 0 | 1
2026-05-09 | 0 | 0 | 0 | 0
2026-05-10 | 0 | 0 | 0 | 0
2026-05-11 | 0 | 0 | 0 | 0
2026-05-12 | 0 | 0 | 0 | 0
2026-05-13 | 0 | 0 | 0 | 0
2026-05-14 | 0 | 0 | 0 | 0

## Mega-Project Failures
Discipline | Inspection Outcome | Inspection Type | Failure Date | Days Since Failure | Address | Quadrant | Community | Deficiency Text | Project Cost | Project Description | Permit Class | Work Class | Permit Status | Parent BP Permit ID | Parent BP Match | Job Type | Mega Project Flag | Tax Appeal Pending? | Federal Vendor? | AGLC Licence At Address? | Federal Sole-Source Vendor? | Recently Opened Here?
Building Deficiencies | Not Acceptable | Progress | 2026-04-27 | 17 | #259C 6455 MACLEOD TR SW | SW | MEADOWLARK PARK | NBC AE Division B 3.1.17. Occupant Load - Provide a permanent sign posted in a conspicuous location indicating that the maximum occupant load is 58 people. | 1000000 | Interior Alterations - Restaurant | 3608 - Restaurant | Alteration | Completed | BP2025-17324 | YES | Commercial / Multi Family Project | YES

## READ ME
Shovel Radar
Run date: 2026-05-14
CONFIDENTIAL — Shovel Radar. This report is licensed to the named subscriber only. Redistribution, resale, or sharing with third parties is strictly prohibited.
Tab | Description
All Failed Inspections | Inspection Failure Alerts — All Disciplines — Run date: 2026-05-14 ¦ 9 failures
Building Deficiencies | Building Deficiencies — GCs / framing / drywall — Same-week-call rework leads
Electrical Deficiencies | Electrical Deficiencies — electrical subs / wholesalers — Failed electrical inspections, with deficiency text
P&G Deficiencies | Plumbing & Gas Deficiencies — plumbing subs / wholesalers — Failed P & G inspections, with deficiency text
Repeat Offenders | Repeat Offenders — Contractors with ≥2 failures in the window
Daily Volume Trend | Daily Volume Trend — Failures per day — staffing input for rework shops
Mega-Project Failures | Mega-Project Failures — Parent BP ≥ $1M — high-stakes rework
** THIS IS A 5-ROW ANONYMIZED SAMPLE **
The full subscriber workbook contains every active row in this data slice with contact columns populated. Subscribe at shovelradar.com/pricing or book a 15-minute fit call.

## Gatekeeper Scripts
How to Bypass the Front Desk
Commercial permits that failed inspection. The GC has 7-14 days to fix the deficiency before re-inspection — they need a rework specialist NOW.
The Cold-Call Opener
“Hi, calling about the failed inspection at [Address]. I'm a [your trade] — I do a lot of rework on Calgary commercial sites and can get on-site within 24 hours. Has [Contractor Name] got someone lined up to fix the deficiency before re-inspection?”
If they ask 'What's this regarding?'
“Rework on the failed inspection at [Address]. Site super or PM, urgent.”
If they say 'Send an email instead'
“Best email? Quick — when's the re-inspection scheduled? I'll work back from that to commit a crew.”
Why this opener works
Same-week urgency. The GC has a hard deadline. Asking about the re-inspection date signals you're going to actually deliver, not just bid.